## ListOfFeatures
Product Backlog - Project Title (List of your features)
User Stories / List of features
As a stafff, i am able to login and check messages, create contracts, edit and delete.
As a site visitor, I have the possibility to contact for more information.
As a site visitor, i am able to send a request to apply for an apartment.
As a site visitor, I am able to subscribe to newsletters to remain upto date.
As a site visitor i can send a request to terminate my agreement

## sprint1
Sprint Backlog : Sprint 1 Feb 7 - Feb 11
BACKLOG TASK & ID | STORY POINTS (NR) | ASSIGNED TO | STATUS
User Story/ Feature #1
Universal Header and footer |  | Suraj | Completed
Designing database |  | sandu | Completed
create github repo |  | everyone | Completed
Scrum editing and uploading |  | vignesh | Completed
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
During this week, you should update your exisiting pages that is your pages have universarl header and footer.
Upload this excel file to your project Repo in GitHub and update it regulaly.
You have planned your features and have distributed work among your team members
You have designed your database. Make sure that each member has his/her own table to work with.
You have create a GitHub repo and each member is added as collaborator.
Please make regular commits and get familiar with the development activities by utilizing version control.
Uploaing your files to GitHub repo is not acceptable. It will have negative impact on your grade.
Ask questions during the consultation sessions if you are not sure about how you are proceeding

## sprint2
Sprint Backlog : Sprint 2 (Feb 14 - Feb 18)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing
Task : List products based on categories | 2 | Juha
Task : Search products | 4 | Johanna
Task: Display products | 2 | Markku
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.

## sprint3
Sprint Backlog : Sprint 3 (Feb 21 - Feb 25)
BACKLOG TASK & ID | STORY POINTS | ASSIGNED TO | STATUS
User Story #1
Task : Make a list of categories of products | 2 | Pekka | Ongoing
Task : List products based on categories | 2 | Juha
Task : Search products | 4 | Johanna
Task: Display products | 2 | Markku
User Story #2
Task
Task
Task
Task
User Story #3
Task
Task
Task
Task
User Story #4
Task
Task
Task
Task
User Story #5
Task
Task
Task
Task
TOTAL
Hints:
You are working on tasks that you have been assigned to in your team.
You are present in your team meetings.
You are familiary with the GitHub repo for your project work.
You are doing regular commits and you have the latest version of the website in your local device.
Finalize your work and start to preare for the project review.
Make sure that your repository, shell.hamk.fi servers all have the latest version of your website.